## Slide 1
SCENARIO 09 · EXAMPLE · Q2 2026 QBR
Atlas Q2 2026 QBR
Leadership review — freeze, silicon, farm; people yellow carried
Pattern: Leadership QBR scorecard → risks → asks
EXAMPLE · Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Cover (example). Q2 green overall; carry people risk; ask Q3 plan + HC.
Leadership QBR scorecard → risks → asks
SRE Book — example postmortem (impact honesty): https://sre.google/sre-book/example-postmortem/
EM Tools — executive communication updates: https://www.em-tools.io/engineering-manager-responsibilities/executive-communication

## Slide 2
WHERE THIS DECK SHAPE COMES FROM
Pattern provenance
Public pattern (structure only — not a confidential company deck):
Leadership QBR scorecard → risks → asks
• SRE Book — example postmortem (impact honesty)
https://sre.google/sre-book/example-postmortem/
• EM Tools — executive communication updates
https://www.em-tools.io/engineering-manager-responsibilities/executive-communication
How to use: copy section order and decision verbs; replace with your metrics.
In-repo: skills/presentations/classic-public-cases.md
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Leadership QBR scorecard → risks → asks
SRE Book — example postmortem (impact honesty): https://sre.google/sre-book/example-postmortem/
EM Tools — executive communication updates: https://www.em-tools.io/engineering-manager-responsibilities/executive-communication

## Slide 3
READ THIS BEFORE THE DETAILS
Situation & decision card
Presenter: Alex Chen — EM, Atlas Q2 QBR
Decision-maker: Morgan Lee + leadership forum
Audience: VP Eng, peer EMs, program
What just happened / context:
Q2 closed ~2026-06-26 lookback: AON B 3/20, freeze 4/10, TO 4/28, day-3 boot 5/15, sample on track 6/30. USB3 partial; unplanned ~20%; IO single-thread carried yellow.
Stakes if we get this wrong:
If leadership only hears GREEN silicon, they may underfund Q3 hire/intake discipline and recreate unplanned overload.
Decision needed:
Endorse next priorities P1 sample SLA + P2 revB; keep WiFi stretch; support DV hire + Q3 plan B.
Recommendation: Overall GREEN with explicit carry risks; approve P1/P2 and HC path.
If YES: Q3 kickoff (08) has air cover; hire continues; intake rule enforced.
If NO / delay: Same single-thread risk into sample support peak.
Decide by: This QBR (~2026-06-26) + follow-up into 7/01 kickoff
Arc prior: H1 arc so far: 01→02→03/06→04→05→07 (not 08 — Q3 kickoff is after this QBR)
Arc next: 08 Q3 kickoff 7/01 under endorsed commits
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Agent/human: answer who/stakes/decision from this slide alone. Recommend=Overall GREEN with explicit carry risks; approve P1/P2 and HC path. by This QBR (~2026-06-26) + follow-up into 7/01 kickoff.

## Slide 4
BOTTOM LINE UP FRONT
BLUF — Q2 overall GREEN
Overall: GREEN · Wins: freeze 4/10, day-3 boot 5/15, farm ROI · Carry: IO single-thread · Ask: Q3 B + HC
Q2 lookback (QBR ~2026-06-26): AON Option B (3/20); RTL freeze 4/10; TO 4/28; day-3 boot 5/15; sample plan on track 6/30.
Miss/partial: USB3 complete (to 6/10) — capacity unplanned ~20%.
Next: endorse Q3 balanced plan + senior DV req (opened 5/22).
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: QBR classic close.

## Slide 5
Scorecard vs commits
AON freeze-ready decision — Hit — B approved 3/20
RTL freeze 4/10 — Hit
Day-5 boot — Hit — day 3 actual (silicon 5/12)
USB3 bring-up done Q2 — Partial — 6/10 forecast
0 attrition — Hit
Unplanned ≤15% — Miss — actual ~20%
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Same commits as kickoff.

## Slide 6
What slipped & why
Assumption broken: unplanned load would stay ≤15%; board+ECO-22 consumed more.
Mid-Q we chose sample path over USB3 perfection (correct call).
Change Q3: +1 DV; stricter intake; unplanned budget 15% explicit in plan.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: System fix, not blame.

## Slide 7
Risks into next period
1. IO DV single-thread — +1 hire / contractor bridge — Alex
2. Sample customer change requests — intake rule — Alex+PM
3. HelixSim PO timing — procurement 6/05 — Finance
Lookback A: outcomes 62% / invest 18% / unplanned 20%.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Owned carry-forward.

## Slide 8
Options & recommendation
Compare paths; recommendation is marked REC. Decision owner picks by the date on the Ask slide.
Next priority | Why | Capacity note
P1 Sample SLA (REC) | Design-win | Fits A with hire
P2 RevB AON | Tech residual | Investment band
P3 WiFi stretch | Optional | Only if P1 green
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Walk trade-offs; land recommendation.

## Slide 9
WHAT WE NEED FROM THIS ROOM
Decision & ask
Three takeaways: freeze+boot green; unplanned drove USB3 partial; support Q3 B + DV hire.
Endorse P1/P2; WiFi remains stretch.
Decisions by: this QBR (~6/26) + follow-up 1:1 into Q3 kickoff 7/01.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: QBR classic close.