## Slide 1
SCENARIO 03 · EXAMPLE · ATLAS HEALTH
Atlas Platform — Q2 org effectiveness
1:1 pack for Morgan Lee — delivery green, people yellow
EXAMPLE · Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Cover (example). Atlas healthy on delivery; yellow on IO DV single-thread → endorse hire.

## Slide 2
BOTTOM LINE UP FRONT
BLUF — delivery green, capacity tight
Delivery: GREEN · People: YELLOW · Ask: endorse +1 DV req (see resource deck)
Mandate: own Aurora integration DV + first-silicon bring-up for NovaSemi connectivity SoC.
Outcomes: (1) RTL freeze held 4/10 (2) day-3 boot 5/15 (3) DV farm ROI visible.
Top risk: single-threaded on high-speed IO DV (Priya overloaded); backup is junior only.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: One ask; point to deck 06 for business case.

## Slide 3
Outcomes vs commits
Freeze-ready AON decision — Hit — Option B landed Mar 20
RTL freeze 4/10 — Hit — held
Day-5 boot target — Hit — actual day 3 (silicon 5/12)
USB3 bring-up complete — Partial — stable path slipped to June 10
Team voluntary attrition — Hit — 0 exits in Q2
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Honest partial on USB3.

## Slide 4
Capacity reality (context A)
Q2 actual mix (Atlas 12 FTE):
• Planned Aurora outcomes ~62%
• Tech investment (DV farm, assertions) ~18%
• Unplanned (board issues, ECO-22) ~20% ← above 10–15% plan
Unplanned overrun is why USB3 is partial — not thrash for its own sake.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Explain A vs planned; HC uses B in deck 06.

## Slide 5
People & capability
Critical path: Priya (HS IO DV) has no senior backup.
Mina (analog liaison) 0.5 FTE borrowed from IP team through mid-Q2.
Hiring: 1 req open 4 weeks — pipeline thin for senior DV.
Ask is structural, not a complaint: protect sample path with +1 DV.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Facts + ask, no blame.

## Slide 6
Options & recommendation
Compare paths; recommendation is marked REC. Decision owner picks by the date on the Ask slide.
Ask type | What changes | If deferred
+1 DV (REC) | Backup Priya; USB3 + sample surge | USB3 slip & burnout risk
Reprioritize only | Drop non-Aurora support | Partner friction
None | Continue | Accept yellow people risk
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Walk trade-offs; land recommendation.

## Slide 7
WHAT WE NEED FROM THIS ROOM
Decision & ask
Primary ask: Endorse opening senior DV requisition (detail in resource request ~2026-05-20).
Decision by: 2026-05-18 1:1 (after first-silicon readout).
Air cover: restate Aurora sample > internal tool polish in Thursday steering.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: One ask; point to deck 06 for business case.