## Slide 1
SCENARIO 08 · EXAMPLE · Q3 2026 KICKOFF
Atlas Q3 2026 period commit
Kickoff after sample path — revB + harden
EXAMPLE · Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Cover (example). Q3 kickoff balanced: sample+revB commit, WiFi stretch.

## Slide 2
BOTTOM LINE UP FRONT
BLUF — endorse balanced Q3 plan (Option B)
Period goal: sample support + revB AON start · Ask: Endorse Option B on 2026-07-01 kickoff
COMMIT: Tier-1 sample support SLA (samples shipped 6/30); revB AON dual-mux RTL start; USB3 closed.
STRETCH: WiFi IP bring-up spike.
OUT: sensor hub; second customer custom board.
Assumes +1 DV offer accepted by mid-July (req opened ~5/22).
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Balanced commit with stretch labeled.

## Slide 3
Outcomes & success metrics
1. Sample support — critical tickets < 48h response — owner Alex
2. RevB AON dual mux — RTL ready review 9/15 — owner clock guild
3. USB3 — exit criteria signed 7/15 — owner Priya (+ new DV)
Stretch: WiFi IP smoke on FPGA — only if sample green.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Clear commit/stretch/out.

## Slide 4
Milestones & working agreements
Milestones after sample: 7/15 USB3 exit · 8/01 WiFi gate · 9/15 revB RTL review
Weekly Atlas ops Mon; steering Thu; yellow risks in BLUF form to Morgan same day.
Intake rule from H2 roadmap remains law.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: OS + gates.

## Slide 5
Options & recommendation
Compare paths; recommendation is marked REC. Decision owner picks by the date on the Ask slide.
Plan option | Scope | Risk | Resource need
A Aggressive | Sample+revB+WiFi full | High | +1 must + contractor
B Balanced (REC) | Sample+revB; WiFi stretch | Med | +1 as planned
C Conservative | Sample only | Low | Current only
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Walk trade-offs; land recommendation.

## Slide 6
WHAT WE NEED FROM THIS ROOM
Decision & ask
Endorse Option B for Atlas Q3 2026.
Confirm Morgan air cover on intake rule.
HC path: keep senior DV req on track (deck 06).
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Balanced commit with stretch labeled.