## Slide 1
SCENARIO 02 · EXAMPLE · FIRST SILICON
Aurora first silicon: day-3 boot achieved
Bring-up readout for VP Eng + program — sample path unlocked
Pattern: Launch / silicon bring-up readout (impact first)
EXAMPLE · Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Cover (example). First silicon day-3 boot → ask for Tier-1 sample plan approval.
Launch / silicon bring-up readout (impact first)
MediaTek public 2nm tape-out milestone language: https://www.mediatek.com/press-room/mediatek-develops-chip-utilizing-tsmcs-2nm-process-achieving-milestones-in-performance-andpower-efficiency
SRE Book — example postmortem impact summary shape: https://sre.google/sre-book/example-postmortem/

## Slide 2
WHERE THIS DECK SHAPE COMES FROM
Pattern provenance
Public pattern (structure only — not a confidential company deck):
Launch / silicon bring-up readout (impact first)
• MediaTek public 2nm tape-out milestone language
https://www.mediatek.com/press-room/mediatek-develops-chip-utilizing-tsmcs-2nm-process-achieving-milestones-in-performance-andpower-efficiency
• SRE Book — example postmortem impact summary shape
https://sre.google/sre-book/example-postmortem/
How to use: copy section order and decision verbs; replace with your metrics.
In-repo: skills/presentations/classic-public-cases.md
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Launch / silicon bring-up readout (impact first)
MediaTek public 2nm tape-out milestone language: https://www.mediatek.com/press-room/mediatek-develops-chip-utilizing-tsmcs-2nm-process-achieving-milestones-in-performance-andpower-efficiency
SRE Book — example postmortem impact summary shape: https://sre.google/sre-book/example-postmortem/

## Slide 3
BOTTOM LINE UP FRONT
BLUF — first silicon green on critical path
Status: GREEN · Day-3 Linux boot on A0 (silicon 5/12) · Ask: sample plan for 6/30
Outcome: Aurora A0 (fab return 2026-05-12) brought up; UART + DDR + Linux prompt on day 3 (target day 5).
Impact: unlocks Tier-1 sample commit for end of June; de-risks H2 design-win demo.
Residual: USB3 not yet stable (ECO-22); not on sample critical path.
Prior: AON Option B (3/20) held RTL freeze 4/10 → tape-out 4/28 → this bring-up.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Celebrate briefly; land sample approval.

## Slide 4
Goal recall (period start)
Q2 commit (period-start deck): first silicon bring-up with day-5 boot target; UART+DDR minimum for internal validation.
Definition of done unchanged — no goalpost move.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Same DoD as kickoff.

## Slide 5
Outcome metrics
Boot day: target ≤5 / actual 3 (Δ −2 days)
Critical open bugs at handoff: target ≤5 / actual 4
AON sleep-exit (from tech review B): pass on 2/3 corners; cold corner in flight
Power (idle AON): target ≤2.1 mW / measured 1.9 mW at iso-perf
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Lead with boot and sample path.

## Slide 6
How we got here + learnings
1. Phased AON clock (Option B, decided 3/20) held freeze 4/10 — paid off in clean bring-up.
2. Pre-silicon FPGA catch of DDR training bug avoided day-1 hang.
3. Shared DV farm cut regression from 18h → 6h (see benefit deck).
Keep: freeze discipline. Stop: ad-hoc board rework without ECO. Start: sample checklist owner.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Connect back to prior decisions.

## Slide 7
Options & recommendation
Compare paths; recommendation is marked REC. Decision owner picks by the date on the Ask slide.
Next step | Owner | Date | Note
Customer sample plan (REC) | Alex + PM | 2026-05-22 | Needs Morgan approve
USB3 stabilize | IO team | 2026-06-10 | Not sample-blocking
Cold-corner AON retest | Priya | 2026-05-25 | From tech residual
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Walk trade-offs; land recommendation.

## Slide 8
WHAT WE NEED FROM THIS ROOM
Decision & ask
Ask: Approve customer sample plan targeting 2026-06-30 shipment to Tier-1.
Owner: Morgan Lee endorsement; Alex executes checklist.
By: 2026-05-22 steering (presentation date ~2026-05-16).
No HC ask here (see resource deck if sample surge).
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Celebrate briefly; land sample approval.