## Slide 1
SCENARIO 07 · EXAMPLE · AURORA H2 ROADMAP
Atlas H2 2026 roadmap
Post-sample path: revB, WiFi IP, platform hardening
Pattern: Outcome themes + not-doing + capacity-honest plan
EXAMPLE · Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Cover (example). H2 map with sample-first priority rule.
Outcome themes + not-doing + capacity-honest plan
EM Tools — Roadmap planning: https://www.em-tools.io/engineering-manager-responsibilities/roadmap-planning
StaffEng — engineering strategy: https://staffeng.com/guides/engineering-strategy/

## Slide 2
WHERE THIS DECK SHAPE COMES FROM
Pattern provenance
Public pattern (structure only — not a confidential company deck):
Outcome themes + not-doing + capacity-honest plan
• EM Tools — Roadmap planning
https://www.em-tools.io/engineering-manager-responsibilities/roadmap-planning
• StaffEng — engineering strategy
https://staffeng.com/guides/engineering-strategy/
How to use: copy section order and decision verbs; replace with your metrics.
In-repo: skills/presentations/classic-public-cases.md
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Outcome themes + not-doing + capacity-honest plan
EM Tools — Roadmap planning: https://www.em-tools.io/engineering-manager-responsibilities/roadmap-planning
StaffEng — engineering strategy: https://staffeng.com/guides/engineering-strategy/

## Slide 3
READ THIS BEFORE THE DETAILS
Situation & decision card
Presenter: Alex Chen — EM + program PM
Decision-maker: Morgan Lee + steering (endorse map + priority rule)
Audience: Steering: eng, PM, IP/package partners
What just happened / context:
H1 delivered freeze, silicon, sample path. H2 must choose: sample support vs early WiFi IP integrate if capacity conflicts. RevB dual-mux AON still owed from Option B residual.
Stakes if we get this wrong:
Without an explicit priority rule, partner teams will dual-commit Atlas and break sample SLA.
Decision needed:
Endorse H2 themes; confirm default sample > WiFi on conflict.
Recommendation: Endorse map; sample-first; revB AON in investment band; WiFi stretch.
If YES: Intake rule enforceable; partners plan against the same not-doing list.
If NO / delay: Hallway commits return; sample and WiFi thrash.
Decide by: 2026-06-12 roadmap review
Arc prior: 01 residual revB · 02 sample · 04/05 farm/seats · 06 hire
Arc next: 08 Q3 commit locks this map into period plan
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Agent/human: answer who/stakes/decision from this slide alone. Recommend=Endorse map; sample-first; revB AON in investment band; WiFi stretch. by 2026-06-12 roadmap review.

## Slide 4
BOTTOM LINE UP FRONT
BLUF — endorse H2 themes; pick sample vs WiFi priority
Themes: Sample · RevB · Platform · Capacity A planned · Decision: sample > WiFi if conflict
Outcomes H2: (1) Tier-1 sample support (2) revB dual-clock AON (3) WiFi IP integrate-or-park.
Not-doing: new sensor hub SKU support; non-Aurora bring-up consulting.
Ask: endorse map; if conflict, sample path outranks WiFi IP by default.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Endorsed map, not wishlist.

## Slide 5
Now / Next / Later
NOW (through June): sample checklist (ship 6/30), USB3, cold-corner AON.
NEXT (Q3): revB AON dual mux; farm/seat expand; +1 DV ramp.
LATER (Q4): WiFi IP integration or explicit park; next-node exploration spike.
Gates: sample 6/30 · revB RTL target 9/15 · WiFi decision gate 8/01.
Already done earlier H1: AON B (3/20), freeze 4/10, TO 4/28, day-3 boot 5/15.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Time-ordered themes.

## Slide 6
Capacity & assumptions (A)
H2 plan (assuming +1 DV mid-Q3 productive):
• Outcomes ~65%
• Investment (revB, farm) ~20%
• Unplanned ~15%
Assumptions: HelixSim seats land; PMIC revB on time; no second silicon spin.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: A only; HC already requested.

## Slide 7
Intake rule
Partner asks for non-Aurora bring-up help enter only with:
owner + displace (usually non-critical polish) + Alex ack.
Silent hallway commits are invalid — restate in steering.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Protect the map.

## Slide 8
Options & recommendation
Compare paths; recommendation is marked REC. Decision owner picks by the date on the Ask slide.
Priority call | Keep | Displace | Note
Sample vs WiFi (REC sample) | Sample path | WiFi early integrate | Design-win
RevB AON vs polish | RevB dual mux | Nice-to-have tools | From tech residual
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Walk trade-offs; land recommendation.

## Slide 9
WHAT WE NEED FROM THIS ROOM
Decision & ask
Endorse Atlas H2 roadmap as shown.
Confirm default: sample > WiFi on capacity conflict.
Dependency owners: PMIC Ken; Package Rui; WiFi IP lead Sam.
Atlas Platform · Project Aurora · NovaSemi · 2026
Notes: Endorsed map, not wishlist.